## Tasklists
Task | Task description | Status | Start Date | Dute Date | Priority | Private | Progress | Status | Status text | Assigned to | Date created | Created by firstname | Created by lastname | Completed date | Completed by firstname | Completed by lastname | Parent task | Completed on time | Priority text | Tags | Workflow Stages
Phase 1 - Project Planning
Define Dataset |  |  | 2024-09-26 | 2024-09-27 | 1 | 0 | 0 | new | not started | Anyone | 2024-09-26 19:52 | Hugo | Liz Lau |  |  |  |  | FALSE | High priority | Project Management | Complete
Setup Git Collaboration |  |  | 2024-09-26 | 2024-09-27 | 1 | 0 | 0 | new | not started | Anyone | 2024-09-26 19:52 | Hugo | Liz Lau |  |  |  |  | FALSE | High priority | In progress | To do
• Team members verify Git pull, branch, request works | Team members verify they can commit, push, branch, pull/review of github project repository |  | 2024-09-26 | 2024-09-27 | 1 | 0 | 0 | new | not started | Anyone | 2024-09-26 21:18 | Hugo | Liz Lau |  |  |  | 33460435 | FALSE | High priority
Complete Project Plan Template | Veda to submit project plan template |  | 2024-09-26 | 2024-09-27 | 100 | 0 | 0 | new | not started | Veda bommareddy | 2024-09-26 19:52 | Hugo | Liz Lau |  |  |  |  | FALSE | Medium priority | Planning | Complete
• Submit Draft Project Schedule |  |  | 2024-09-26 | 2024-09-26 | 100 | 0 | 0 | new | not started | Hugo Lau | 2024-09-26 21:17 | Hugo | Liz Lau |  |  |  | 33460429 | FALSE | Medium priority
• Review project plan template |  |  | 2024-09-26 | 2024-09-27 | 100 | 0 | 0 | new | not started | Rob Casey, Hugo Lau | 2024-09-26 21:35 | Hugo | Liz Lau |  |  |  | 33460429 | FALSE | Medium priority
Phase 2 - MVP (Extract, Transform, Load, Docker)
Extract Data |  |  | 2024-09-26 | 2024-09-28 |  | 0 | 0 | new | not started | Anyone | 2024-09-26 21:05 | Hugo | Liz Lau |  |  |  |  | FALSE | No priority
• Static Extraction | [5 empty] | 0 | 0 | new | not started | Anyone | 2024-09-26 21:18 | Hugo | Liz Lau |  |  |  | 33460698 | FALSE | No priority
• Live Extraction | [5 empty] | 0 | 0 | new | not started | Anyone | 2024-09-26 21:19 | Hugo | Liz Lau |  |  |  | 33460698 | FALSE | No priority
• Full Extract |  |  | 2024-09-26 | 2024-09-28 |  | 0 | 0 | new | not started | Anyone | 2024-09-26 21:28 | Hugo | Liz Lau |  |  |  | 33460698 | FALSE | No priority
• Incremental Extract |  |  | 2024-09-26 | 2024-09-28 |  | 0 | 0 | new | not started | Anyone | 2024-09-26 21:28 | Hugo | Liz Lau |  |  |  | 33460698 | FALSE | No priority
Transform Data |  |  | 2024-09-28 | 2024-09-30 |  | 0 | 0 | new | not started | Anyone | 2024-09-26 21:24 | Hugo | Liz Lau |  |  |  |  | FALSE | No priority
• 3 Transformation Techniques |  |  | 2024-09-28 | 2024-09-30 |  | 0 | 0 | new | not started | Anyone | 2024-09-26 21:25 | Hugo | Liz Lau |  |  |  | 33460741 | FALSE | No priority
• 5 Transformation Techniques |  |  | 2024-09-28 | 2024-09-30 |  | 0 | 0 | new | not started | Anyone | 2024-09-26 21:25 | Hugo | Liz Lau |  |  |  | 33460741 | FALSE | No priority
• 7 Transformation Techniques |  |  | 2024-09-28 | 2024-09-30 |  | 0 | 0 | new | not started | Anyone | 2024-09-26 21:29 | Hugo | Liz Lau |  |  |  | 33460741 | FALSE | No priority
Load Data |  |  | 2024-09-28 | 2024-10-01 |  | 0 | 0 | new | not started | Anyone | 2024-09-26 21:26 | Hugo | Liz Lau |  |  |  |  | FALSE | No priority
• Load Data --> Full Load |  |  | 2024-09-30 | 2024-10-01 |  | 0 | 0 | new | not started | Anyone | 2024-09-26 21:26 | Hugo | Liz Lau |  |  |  | 33460748 | FALSE | No priority
• Load Data --> Incremental Load |  |  | 2024-09-30 | 2024-10-01 |  | 0 | 0 | new | not started | Anyone | 2024-09-26 21:26 | Hugo | Liz Lau |  |  |  | 33460748 | FALSE | No priority
• Load Data --> Upsert Load |  |  | 2024-09-30 | 2024-10-01 |  | 0 | 0 | new | not started | Anyone | 2024-09-26 21:27 | Hugo | Liz Lau |  |  |  | 33460748 | FALSE | No priority
Phase 3 - (Build Docker Image and Run on AWS)
Build and Run Docker Locally |  |  | 2024-10-01 | 2024-10-01 |  | 0 | 0 | new | not started | Anyone | 2024-09-26 21:32 | Hugo | Liz Lau |  |  |  |  | FALSE | No priority
• Build a docker image using a Dockerfile (the teaching staff will be verifying that the docker image builds locally) |  |  | 2024-10-01 | 2024-10-01 |  | 0 | 0 | new | not started | Anyone | 2024-09-26 21:36 | Hugo | Liz Lau |  |  |  | 33460783 | FALSE | No priority
• Docker container runs locally (the teaching staff will be verifying that the docker image runs locally) |  |  | 2024-10-01 | 2024-10-01 |  | 0 | 0 | new | not started | Anyone | 2024-09-26 21:36 | Hugo | Liz Lau |  |  |  | 33460783 | FALSE | No priority
Deploy docker container to Amazon Web Services (provide screenshot evidence of services configured/running) |  |  | 2024-10-01 | 2024-10-03 |  | 0 | 0 | new | not started | Anyone | 2024-09-26 19:52 | Hugo | Liz Lau |  |  |  |  | FALSE | No priority
• Relational Database Service (RDS) - screenshot of dataset in target storage | screenshot of dataset in target storage |  | 2024-10-01 | 2024-10-03 |  | 0 | 0 | reopened | not started | Anyone | 2024-09-26 21:43 | Hugo | Liz Lau |  |  |  | 33460442 | FALSE | No priority
• Elastic Container Registry (ECR) - screenshot of image in ECR | screenshot of image in ECR |  | 2024-10-01 | 2024-10-03 |  | 0 | 0 | new | not started | Anyone | 2024-09-26 21:43 | Hugo | Liz Lau |  |  |  | 33460442 | FALSE | No priority
• Elastic Container Registry - screenshot of image in ECR | screenshot of scheduled task in ECS |  | 2024-10-01 | 2024-10-03 |  | 0 | 0 | new | not started | Anyone | 2024-09-26 21:43 | Hugo | Liz Lau |  |  |  | 33460442 | FALSE | No priority
• S3 for `.env` file - screenshot of `.env` file in S3 |  |  | 2024-10-01 | 2024-10-03 |  | 0 | 0 | new | not started | Anyone | 2024-09-26 21:43 | Hugo | Liz Lau |  |  |  | 33460442 | FALSE | No priority
• IAM Role - screenshot of created role |  |  | 2024-10-01 | 2024-10-03 |  | 0 | 0 | new | not started | Anyone | 2024-09-26 21:44 | Hugo | Liz Lau |  |  |  | 33460442 | FALSE | No priority
Phase 4 (Testing/Logging, Documentation/Presentation)
Write pipeline metadata logs to a database table |  |  | 2024-10-03 | 2024-10-04 |  | 0 | 0 | new | not started | Anyone | 2024-09-26 21:55 | Hugo | Liz Lau |  |  |  |  | FALSE | No priority
Implement unit tests using PyTest or similar |  |  | 2024-10-03 | 2024-10-05 |  | 0 | 0 | new | not started | Anyone | 2024-09-26 21:56 | Hugo | Liz Lau |  |  |  |  | FALSE | No priority
Documentation |  |  | 2024-10-03 | 2024-10-07 |  | 0 | 0 | new | not started | Anyone | 2024-09-26 21:56 | Hugo | Liz Lau |  |  |  |  | FALSE | No priority
• Code documentation using Python docstrings and comments where reasonable |  |  | 2024-10-03 | 2024-10-07 |  | 0 | 0 | new | not started | Anyone | 2024-09-26 21:57 | Hugo | Liz Lau |  |  |  | 33461587 | FALSE | No priority
• Markdown documentation explaining the project context, architecture and installation/running instructions |  |  | 2024-10-03 | 2024-10-07 |  | 0 | 0 | new | not started | Anyone | 2024-09-26 21:58 | Hugo | Liz Lau |  |  |  | 33461587 | FALSE | No priority
Presentation |  |  | 2024-10-07 | 2024-10-07 |  | 0 | 0 | new | not started | Anyone | 2024-09-26 21:59 | Hugo | Liz Lau |  |  |  |  | FALSE | No priority
• Project context and goals | [5 empty] | 0 | 0 | new | not started | Anyone | 2024-09-26 22:00 | Hugo | Liz Lau |  |  |  | 33461599 | FALSE | No priority
• Datasets selected |  |  | 2024-10-07 | 2024-10-07 |  | 0 | 0 | new | not started | Anyone | 2024-09-26 22:00 | Hugo | Liz Lau |  |  |  | 33461599 | FALSE | No priority
• Solution architecture diagram using draw.io or similar |  |  | 2024-10-07 | 2024-10-07 |  | 0 | 0 | new | not started | Anyone | 2024-09-26 22:00 | Hugo | Liz Lau |  |  |  | 33461599 | FALSE | No priority
• ELT/ETL techniques applied |  |  | 2024-10-07 | 2024-10-07 |  | 0 | 0 | new | not started | Anyone | 2024-09-26 22:00 | Hugo | Liz Lau |  |  |  | 33461599 | FALSE | No priority
• Final dataset and demo run (if possible) |  |  | 2024-10-07 | 2024-10-07 |  | 0 | 0 | new | not started | Anyone | 2024-09-26 22:00 | Hugo | Liz Lau |  |  |  | 33461599 | FALSE | No priority
• Lessons learnt |  |  | 2024-10-07 | 2024-10-07 |  | 0 | 0 | new | not started | Anyone | 2024-09-26 22:00 | Hugo | Liz Lau |  |  |  | 33461599 | FALSE | No priority